## UX Overhaul
Phase | Source plan file | Implementer model | Reviewer model | Reasoning
Plan 1A — Foundation Setup | 2026-04-28-ux-overhaul-foundation-setup.md | Sonnet | Opus | Foundation work: aiosqlite migration for the user_preferences table, JWT role-claim parsing, design-token CSS, prefs server module + endpoints. Schema and auth-claim mistakes are expensive to undo once data lands, so spend once on Opus review even though Sonnet handles the implementation comfortably.
Plan 1B — Static Chrome | 2026-04-28-ux-overhaul-static-chrome.md | Haiku | Haiku | Four pure-presentational vanilla-JS components (top-nav, version-chip, avatar, layout-icon), each ≤100 LOC, no state, no async, no server interaction. Pattern is repetitive and the safe-DOM rules are explicit. Cheapest tier on both sides; the review just spot-checks for innerHTML and pattern adherence.
Plan 1C — Stateful Chrome | 2026-04-28-ux-overhaul-stateful-chrome.md | Sonnet | Sonnet | Prefs client (localStorage cache + 500ms debounced PUT), telemetry helper (fire-and-forget), avatar/layout popovers with click-outside + Escape. Subtle async + event-lifecycle but well-bounded. Sonnet/Sonnet — popover bugs are visible and easy to spot at this tier; Opus is overkill.
Plan 2A — Document Card + Density Modes | 2026-04-28-ux-overhaul-document-card.md | Haiku | Sonnet | Presentational card component with three density modes driven by CSS variables and MFPrefs. Implementation is mechanical given the explicit mockups, but bumping reviewer to Sonnet because density toggle interacts with the prefs system landed in 1C — worth verifying the binding is correct, not just the visuals.
Plan 2B — Card Interactions | 2026-04-28-ux-overhaul-card-interactions.md | Sonnet | Sonnet | Hover preview popover, right-click context menu, multi-select observable state, bulk action bar, folder-browse page wrapping it all. Multiple interaction systems coexisting without listener leaks is the failure mode here. Sonnet handles the orchestration; Sonnet review catches missed cleanup paths.
Plan 3 — Search-as-Home Page | 2026-04-28-ux-overhaul-search-as-home.md | Sonnet | Sonnet | Feature-flagged replacement of static/index.html with three layout modes (Maximal / Recent / Minimal). Both flag-on and flag-off paths must work — flag-off keeps legacy Convert page live, so rollback is cheap. Not security-critical, doesn't touch DB or auth, so Sonnet/Sonnet is the right floor.
Plan 4 — IA Shift | 2026-04-28-ux-overhaul-ia-shift.md | Sonnet | Opus | New /api/me endpoint, real role binding via UnionCore JWT (replaces the hardcoded role='admin' placeholder), Activity dashboard gated by core.auth.Role. This is the auth surface — role-gating bugs are security issues. Opus reviewer once to verify the gate is enforced on every protected endpoint, not just the obvious ones.

## System Unifier
Phase | Source plan file | Implementer model | Reviewer model | Reasoning
Phase 0 — Pre-flight reconnaissance (Tasks 0.1–0.7) | 2026-04-28-active-operations-registry.md | Haiku | Haiku | Read-only discovery: trace existing pipeline.py, scan_coordinator.py, bulk_worker.py, lifecycle_scanner.py to confirm assumptions about cancel signals and lifecycle hooks. Output is notes, not code. Cheapest tier on both sides; Haiku is good enough for summarising existing module behaviour against the plan's assumptions.
Phase 1 — Registry + DB foundation (Tasks 1–10) | 2026-04-28-active-operations-registry.md | Opus | Opus | Load-bearing concurrency primitive: new core/active_ops.py (in-memory dict + write-through to a new active_operations SQLite table), lifespan hooks, scheduler integration, singleton lifecycle. Every later phase depends on this being correct — race conditions or write-through gaps cascade across all six worker subsystems. Spend tokens here; it is genuinely the highest-risk slice of the whole plan.
Phase 2 — HTTP API (Tasks 11–13) | 2026-04-28-active-operations-registry.md | Sonnet | Sonnet | Single GET /api/active-ops endpoint feeding three frontend surfaces. Standard FastAPI pattern with a strict response schema. Risk is contract drift between this payload and Phase 4's three consumers — Sonnet reviewer is sufficient because the payload is small and reviewable in one screen.
Phase 3 — Worker retrofits (Tasks 14–23) | 2026-04-28-active-operations-registry.md | Opus | Sonnet | Touches six worker modules (pipeline, scan_coordinator, trash, analysis, lifecycle_scanner, bulk_worker) to register/update/finish operations and bridge cancel signals to each subsystem's native mechanism. The structural traps — double-register, missed cleanup on exception paths, cancel hook never firing — need Opus to catch on the implementer side. Reviewer drops to Sonnet to control cost; the implementer does the heavy thinking.
Phase 4 — Frontend (Tasks 24–34) | 2026-04-28-active-operations-registry.md | Sonnet | Haiku | Three presentational surfaces (sticky banner, per-page inline widget, Status hub) all fed by the /api/active-ops payload from Phase 2. Once that contract is stable the work is mechanical DOM construction + polling. Haiku reviewer is fine — visual diff against mockups is exactly what cheap models do well.
Phase 5 — Cleanup + documentation (Tasks 35–46) | 2026-04-28-active-operations-registry.md | Sonnet | Sonnet | Removing dead per-subsystem progress code that the registry now subsumes, plus CLAUDE.md / version-history.md / whats-new.md updates. Deletions are irreversible — judgement about what's truly subsumed vs. what still has unique callers needs Sonnet, not Haiku. Sonnet reviewer catches the cases where the implementer was over-eager.

## Legend
Model legend & cost guidance
Model | Use for | Approx cost vs Opus
Haiku | Pattern-driven scaffolding, presentational vanilla-JS components, doc edits, read-only discovery, visual diff review. | ≈ 1/15
Sonnet | Most feature work: FastAPI endpoints, vanilla-JS with state, multi-system interactions, judgement-call cleanup. | ≈ 1/5
Opus | Concurrency primitives, schema/migration design, auth surface, cancel-propagation across subsystems. | 1×
Heuristic | Default both implementer and reviewer to Sonnet. Justify every upgrade to Opus (irreversibility, security, concurrency) and every downgrade to Haiku (mechanical, well-spec'd, low blast radius).